## Sheet1
Appendix A - ETR TIMELINE
| Drafting |  |  | Reviewing |  |  | Updating |  | Final versions |  | Finalization
| Draft writing | Draft sending | Publication on the Drive | Informing the ETR RC | Informing UEMS Bodies/NMAs | Reviewing of the documents | Responding to comments | Updating of the draft ETRs | Final versions sending | Circulation of the ETRs | Presentation | Discussion and Vote | Follow up actions
To do | Sections draft their ETRs | Sections send the drafts to the UEMS Office - coordination@uems.eu | The UEMS Office publishes the draft ETRs on the Google Drive: | The UEMS Office informs the ETR RC of the availability of the draft ETRs on the Drive | The UEMS Office informs UEMS Bodies and NMAs of the availability of the draft ETRs on the Drive | The ETR RC and related specialty sections review the documents and insert comments in the tables (one in each folder) | The authors of the ETR respond to the comments they received | The authors of the ETR update the documents based on the comments they received | The authors of the ETRs send the final versions of the documents | The UEMS Office (MB) publishes the ETRs on the UEMS website with the other Council supporting documents | The authors of the ETRs present their ETRs during the Advisory Board and Council meetings | Sections and NMAs discuss and vote on the ETRs | Update of the ETRs based on the decisions made by the Council | Numbering of the ETRs Publication on the UEMS website, ETRs page
|  |  | https://drive.google.com/drive/folders/1nu8kjoD3RFtSrODHmJlRWqoXK2fqF81J | [10 empty] | https://www.uems.eu/areas-of-expertise/postgraduate-training/european-standards-in-medical-training
Who | UEMS Bodies | UEMS bodies | UEMS Office (MB) | UEMS Office (MB) | UEMS Office (MB) | ETR RC | ETR authors | ETR authors | ETR authors | UEMS Office (MB) | ETR Authors | Sections and NMAs | ETR Authors and ETR RC | UEMS Office (MB)
Duration | 3 months | 1 day | 1 day | 1 day | 1 day | 1 month | 1 month | 1 month | 1 day | 1 day | 2 days | 2 days | 1 week | 1 day
Deadlines | Three months prior to the Council |  |  | Two months prior to the Council |  |  | One month prior to the Council |  | One month prior to the Council |  | Council meetings |  | One week after the Council