## Sheet1
ETR TIMELINE
What | Drafting |  |  |  | Review of draft ETRs |  | Amendment of ETRs |  | Review of amended ETRs |  | Finalisation
| Draft preparation and submission | Publication of the Draft | Informing the ETR RC | Informing UEMS bodies/NMAs | Review of documents by UEMS bodies and NMAs | Review of documents by the ETR RC | Amendment of ETRs and response to comments | Submission of updated ETR | Review of amended documents by the ETR RC | Publication of amended ETR | Presentation | Vote and discussion | Follow up actions
To do | UEMS bodies draft their ETRs according to UEMS policies and send the ETR draft to the UEMS Office - coordination@uems.eu | The UEMS Office publishes the draft ETRs on the Google Drive: | The UEMS Office informs the ETR RC about the availability of the draft ETRs on the Drive | The UEMS Office informs UEMS bodies and NMAs about the availability of the draft ETRs on the Drive | UEMS bodies and NMAs review the documents and inserts comments in the tables on Google Drive | The ETR RC reviews the documents, has a meeting to discuss the draft ETRs, and inserts comments in the tables on Google Drive | The authors of the ETR respond to the comments they received in the tables on the Drive and amend the documents | The authors of the ETR send the final versions of the documents to the UEMS Office | The ETR RC reviews the amended documents, has a meeting and informs the UEMS Enlarged Executive about its opinion.* | If the ETR is accepted for presentation: The UEMS Office publishes the updated ETRs on the Drive and the UEMS website with the other Council supporting documents | The authors of the ETRs present their ETR at the Advisory Board and Council meetings | Sections and NMAs discuss and vote on the ETRs | Update of the ETRs based on minor comments received during the Council | Numbering of the ETRs Publication on the UEMS website, ETRs page
|  | https://drive.google.com/drive/folders/1nu8kjoD3RFtSrODHmJlRWqoXK2fqF81J | [11 empty] | https://www.uems.eu/areas-of-expertise/postgraduate-training/european-standards-in-medical-training
Who | ETR authors/ UEMS bodies | UEMS Office | UEMS Office | UEMS Office | UEMS bodies, NMAs | ETR RC | ETR authors | ETR authors | ETR RC | UEMS Office | ETR Authors | Sections and NMAs | ETR Authors | UEMS Office (AD)
Deadlines | 4 months before the Council |  |  |  | 3 months before the Council |  | 2 months before the Council |  | 1 month before the Council |  | Council meetings |  | One week after the Council
ETR RC - ETR Review Committee
*not in scheme, but has to follow: decision by UEMS EE if accepted for presentation at Council mtg